## Planner
AACP Convention Backtracking Timetable
CONVENTION PLANNING COMMITTEE: |  |  |  | VP for Conventions (chair) |  | Asst. VP for Conventions |  | As invited: _________________
|  |  |  | NAD Camp Director |  | Registration Chair |  | As invited: _________________
|  |  |  | NAD Camp Coordinator |  | Host Camp Chair |  | As invited: _________________
Month Before Convention
Who is Responsible
14 October |  | VP for Conventions | 1 | Develop Proposed Budget
|  |  | 2 | Obtain options for Convention Location
|  |  | 3 | Contact Possible Host Site(s) for information to present to board
13 November |  | VP for Conventions | 1 | Submit Budget to finance committee and then to the board for OK to present to Business Meeting
|  |  | 2 | Be looking for Assistant VP for Conventions
|  |  | 3 | Select theme for next year's convention
12 December |  | AACP Board | 1 | Selection of next year's convention location
|  |  | 2 | Determine next year's convention dates
|  | VP for Conventions | 3 | Submit name for Assistant VP for Conventions to Board for approval
|  | Finance Chair | 4 | Present convention budget at Business meeting
|  | President | 5 | President announces next year's location and theme at convention
11 January |  | VP for Conventions | 1 | Select Convention Planning Committee
|  | VP for Conventions & NAD Camp Director | 2 | Select First Date for meeting of Convention Planning Committee Conference Call & Set up with NAD Camp Director (at the first meeting, select tentative future committee meeting dates for conference calls)
|  |  | 3 | Negotiate and Finalize contract with host camp
8 April |  | VP for Conventions | 1 | Visit Host Camp, if needed
|  |  | 2 | Determine Convention Layout & Logistics at Host Camp
December Post Convention |  | VP for Conventions | 1 | Verify with Registration Team that all accounts are settled
|  |  | 2 | Call Ultracamp to Release funds to NAD…Attn NAD Camp Director
3
SUB-COMMITTEES FOR AACP CONVENTION
potential members listed by position
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
CHAIR |  | VP Communications |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Members | 1 | AACP Convention 'Registrar' | 1 | VP for Conventions (Elect) | 1 | NAD Resource Coordinator | 1 | Food Service
| 2 | Host Camp 'Registrar' | 2 | AACP President | 2 |  | 2 | Housekeeping/Janitorial
| 3 | E-News Editor | 3 | AACP President-Elect | 3 |  | 3 | Guest Services/Registration
| 4 |  | 4 | Vendor Coordinator | 4 |  | 4
| 5 |  | 5 |  | 5 |  | 5
4
BACKTRACKING TIMETABLE FOR CONVENTION PLANNING TEAMS
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
Chair |  |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Month | # | To Do | # | To Do | # | To Do | # | To Do
FEBRUARY | 1 | CREATE TENTATIVE CONVENTION SCHEDULE
|  |  | 2 | Secure Corporate donors: non-cash…books, gift bags, pens, balloons, high end giveaway, free convention, etc. | 2 | Select Track Leaders: 1) Activities, Attractions & Camp Store 2) Summer Camp Directors 3) Camp Services (Guest Services, Registration, Housekeeping, Janitoria) 4) Camp Spouses 5) Food Service 6) Managers & Executive Directors 7) Summer Camp Staff 8) Ranger, Maintenance, Vehicles 9) New to Camp 10) ACA Accreditation
|  |  | 3 | Work on Convention Theme woven throughout program | 3 | Discuss seminar topic possibilities
MARCH | 1 | WORK WITH NAD CAMP CAMP DIRECTOR IN SECURING GUEST SPEAKER(S)
|  |  | 2 | Select Speaker(s) General Session - finalize $$$ with NAD Camp Director | 2 | Track Leaders contact seminar presenters | 2 | Locate potential 'Local Attractions' for Pre and Post Convention options for attendees & share with E-News
|  |  | 3 | Invite host conference president to speak on opening night |  |  | 3 | Provide airport options to E-News
5
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
Chair |  |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Month | # | To Do | # | To Do | # | To Do | # | To Do
APRIL |  |  | 1 | VENDOR - contact potential vendors for exhibits | 1 | Track Leaders contact seminar presenters
MAY | 1 | FINALIZE CONVENTION SCHEDULE
| 2 | Set up Online Registration with Ultracamp based on Host Camp and Convention Needs | 2 | Secure Music Leader(s) - check with host camp | 2 | Track Leaders contact seminar presenters
| 3 | Provide registration link to E-News | 3 | Select Afterglow Host
|  |  | 4 | VENDOR - contact potential vendors for exhibits
NO SUMMER ASSIGNMENTS
August 20th | AS IT BECOMES AVAILABLE CONTINUE TO PROVIDE INFORMATION TO E-NEWS TO PROMOTE THE CONVENTION
SEPTEMBER |  |  | 1 | Determine Holiday Decorations …work with host camp | 1 | Track Leaders contact seminar presenters | 1 | Provide E-News with 'directions to camp' & 'other information'
|  |  | 2 | Determine any extra signs that are needed for the convention, Work with host camp | 2 | Obtain seminar descriptions
|  |  | 3 | Check with AACP Board for any AACP awards to be presented (Norm Middag Awards, NAD special awards, Retirees, etc)
|  |  | 4 | VENDOR - contact potential vendors for exhibits
6
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
Chair |  |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Month | # | To Do | # | To Do | # | To Do | # | To Do
7 to 8 weeks | 1 | PREPARE LIST OF QUESTIONS FOR ONLINE CONVENTION SURVEY: Big Ideas, Suggestions & Observations, Value
| 2 | Have announcement in E-News about the posting of Job Openings, Wanted, For Sale at the Convention | 2 | Order any special 'freebies' | 2 | Make sure recording devices are functioning properly | 2 | Determine potential Free Time Activities
|  |  | 3 | Vendor Checklist to Host Camp | 3 | Obtain 'needs' list from seminar presenters | 3 | Obtain Vendor List and needs outline from Programming to accommodate them in display area
|  |  | 4 | Work with Host Camp to provide Child Care |  |  | 4 | Locate Child Care providers
[7 empty] | 5 | Provide for a Camp Tour During Convention
5 to 6 weeks | 1 | Locate Welcome - Information Center Host…could be a host camp staff | 1 | Put together 'Good Morning, AACP' morning program features |  |  | 1 | Determine Location of Union Meetings
|  |  | 2 | Plan Communion Service |  |  | 2 | Finalize Evening Recreation
4 weeks | 1 | Communicate with host camp special meals | 1 | VENDOR - final list completed |  |  | 1 | Obtain tentative speciall meal list for food service
| 2 | Communicate with host camp current lodging needs |  |  |  |  | 2 | Obtain current lodging needs list
| 3 | Order name badges
7
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
Chair |  |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Month | # | To Do | # | To Do | # | To Do | # | To Do
3 weeks | 1 | Last minutes items for E-News- Giveaways, etc. | 1 | Last minute Items for E-New | 1 | Last minutes Items for E-News | 1 | Last minute items for E-News
| 2 | Update meal & lodging needs and share with host camp |  |  | 2 | Seminar Presenters: remind about handouts, if needed to be copied ahead of time OR at camp
2 weeks | 1 | SHIP ANY SUPPLIES TO HOST CAMP
| 2 | Print Name Badges | 2 | Print Schedule/ Brochure | 2 | Create packing list | 2 | Finalize PA operation & IT services for general sessions
| 3 | Purchase paper, pens
| 4 | Obtain Tickets for Free Drawing
| 5 | Update meal & lodging needs and share with host camp
1 week | 1 | Update meal & lodging needs and share with host camp | 1 | Prepare Online Convention Survey
1 to 2 days | 1 | Set up Registration |  |  |  |  | 1 | In meeting area, set up "Free Drawing Tables"
| 2 | Set up Membership List Update |  |  |  |  | 2 | Set up meeting rooms
| 3 | Set up Job Openings, For Sale Bulletin Board (work with host camp) |  |  |  |  | 3 | Seminar Presenter needs taken care of
| 4 | Set up welcome - information center with hot drinks, snacks, maps, etc.
8
| REGISTRATION |  | PROGRAMMING |  | EDUCATION |  | HOST CAMP
Chair |  |  | VP for Conventions |  | Asst. VP for Conventions |  | Camp Director or Assigned
Month | # | To Do | # | To Do | # | To Do | # | To Do
CONVENTION | 1 | Register Guests: Include Free Drawing Ticket, map of camp, program brochure, pen, paper, 'freebie gift', etc. | 1 | Open online convention survey | 1 | Set out recording devices | 1 | Oversee Room Assignments
| 2 | Finalize Registration Discrepancies | 2 | Compile Results of Convention Survey (last day) |  |  | 2 | Host Exhibitor Area
| 3 | Prepare attendance summary for AACP Board | 3 | VENDORS: Host Exhibitors |  |  | 3 | Provide for housekeeping needs
DEBRIEF CONVENTION WITH BOARD (during last breakfast)
Post- Convention | 1 | SEND OUT THANK YOU LETTERS: Exhibitors, Presentors, Speakers, Host Camp, Volunteers, Staff, Sponsors, Food Service, etc.
|  |  | 2 | Compile all survey results and share at January's Board Meeting
DISCUSS WAYS TO IMPLEMENT SUGGESTIONS
9

## Sheet2
VP FOR CONVENTIONS RESPONSIBILITIES
1 | Select Asst. VP for Conventions |  | Submit name to be approved by board
2 | Host Site Contracts |  | Work with NAD Camp director in finalizing contracts
3 | Select Guest Speaker(s) |  | Work with NAD Camp director in finalizing contracts
4 | Select Convention Planning Committee: Registration, Advertising, Host Camp, NAD Camp Director, etc.
5 | Call & Chair Meetings |  | Select meeting dates & work with NAD Camp Director to set up conference calls
6 | Serve as Convention Host |  | Oversee Convention Details & Operations
7 | Oversee Budget & Expenses |  | Require receipts of items purchased & process for reimbursement
CONVENTION PLANNING COMMITTEE RESPONSIBILITIES
ADVERTISING & PROMOTION - Website & E-News |  |  |  | PERSON IN CHARGE
1 | 12 months |  | Present Dates & Location at AACP Convention
2 | 9 months |  | Reminder: Dates & Airport
3 | 6 months |  | Ticklers
4 | 4 months |  | Registration Opens
5 | 3 months |  | Accommodations, Attractions, Updates
6 | 2 months | Promoting Event - 2 months | Updates
7 | 1 month |  | Last Minute' Information

## Conf Calls, Purchasing, Reim
Conference Call Procedures
1) | Arrangements for conference calls need to be made with the NAD Camp Director. Normally you will want to make those arrangements a week or more in advance.
2) | Before contacting the NAD Camp Director select several date options and times for the conference call.
3) | Once the date and time is confirmed, share the information committee members.
4) | For PHONE and/or VIDEO-CONFERENCING, contact the NAD Camp Director to make arrangements for this use.
Purchasing & Reimbursements
The VP for Conventions and the NAD Camp Director are responsible for the Convention Budget.
PURCHASES
1 | All purchases must be pre-approved by the VP for Conventions.
2 | When making purchases, keep all of the original receipts and recording on the receipt what the purchases were for (baking class, family art seminar, registration supplies, convention brochures, handout copies for Camp Manager Round Table, etc.)
REIMBURSEMENTS
1 | Number all of your receipts
2 | On a separate sheet of paper, list those receipts. Include:
a) Receipt #
b) Date of Purchase
c) Company Name
d) Item(s) purchases (example: ingredients for cooking class, registration notebooks, etc.)
e) Total all of your receipts
e) Your name and mailing address
3 | Submit (originals or scanned and emailed) to VP for Conventions & NAD Camp Director.
The VP for Conventions will confirm with the NAD Camp Director to provide reimbursments.
10

## Dividers
AACP
CONVENTION
PLANNER
AACP
BOARD
ACTIONS
CONVENTION
SCHEDULES
REGISTRATION
TEAM
PROGRAMMING
TEAM
EDUCATION
TEAM
HOST CAMP
TEAM
OTHER
RESOURCES

## Budgets
Convention Budget Worksheet
Note that the Fees are set per agreement with the host camp and as approved by the AACP Board.
INCOME
Registration Fees
|  | X |  | equals | $
| # attendees - Adults |  | Fee
|  | X |  | equals | $
| # attendees - Children |  | Fee
| 50% ACTUAL AACP DUES |  |  |  | $ |  | Confirm with NAD Camp Director
| Other Income |  |  |  | $
$
$
$
[6 empty] | TOTAL INCOME | $
EXPENSE
Host Camp
|  | X |  | equals | $
| # attendees - Adults |  | Fee
|  | X |  | equals | $
| # attendees - Children |  | Fee
Convention Operations
Pre-Visit
Registration
Programming
Education
Speaker Fees
Printing
Special Travel
Miscellaneous
[6 empty] | TOTAL EXPENSE | $
[6 empty] | ENDING BALANCE | $
13
Convention Budget SAMPLE Worksheet
Note that the Fees are set per agreement with the host camp and as approved by the AACP Board.
INCOME
Registration Fees
| 150 | X | 140 | equals | $ | 21000
| # attendees - Adults |  | Fee
| 32 | X | 70 | equals | $ | 2240
| # attendees - Children |  | Fee
| 50% ACTUAL AACP DUES |  |  |  | $ | 9200 | Confirm with NAD Camp Director
| Other Income |  | Donation |  | $ | 500
$
$
$
[6 empty] | TOTAL INCOME | 32940
EXPENSE
Host Camp
| 150 | X | 130 | equals | $ | 19500
| # attendees - Adults |  | Fee
| 32 | X | 70 | equals | $ | 2240
| # attendees - Children |  | Fee
Convention Operations
|  | Pre-Visit |  |  |  | 750
|  | Registration |  |  |  | 250
|  | Programming |  |  |  | 1500
|  | Education |  |  |  | 800
|  | Speaker Fees |  |  |  | 2500
|  | Printing |  |  |  | 850
|  | Special Travel |  |  |  | 880
|  | Miscellaneous |  |  |  | 330
[6 empty] | TOTAL EXPENSE | 29600
12

## Menu
SAMPLE MENU
| BREAKFAST | LUNCH | SUPPER
Tuesday | AACP Board | AACP Board | AACP Board
| Eggs & Potatoes | Sub Sandwiches | Chili & Cornbread
Wednesday | AACP Board | AACP Board | Lasagna
| Pancakes | Baked Potato Bar
Thursday | Breakfast Burrito | Vegeburgers | Mac & Cheese
Friday | Biscuits & Gravy | Loaf Casserole | Communion Special
Soup, bread, rolls, etc.
Sabbath | Omelettes | Egg Plant Parmesian | Hot Dogs
Sunday | Eggs & Potatoes
MORE IDEAS
| Pancakes | Grilled Cheese | Pan Pizza
| Scrambled Eggs | Macaroni & Cheese | Vege-chicken Pot Pie
| French Toast | Spaghetti | Spaghetti
| Waffles | Sub Sandwiches | Curry & Rice
| Cheese & Eggers | Tostadas | Vegeburgers
| Breakfast Potatoes | Pizza | Manicotti
| Stripples | Tacos | Enchiladas
| Biscuits & Gravy | Quesadillas | Burrito Bar
| Breakfast Burritos | Chicken Pot Pie | Calzones
|  | Vegeburger Loaf | Grilled Cheese
Haystacks
Corn Dogs & Chili
34

## Seating
Sample Seating Arrangements
33

## Vendors
PAST VENDORS
COMPANY | PRODUCTS | CONTACT INRO
SHIRT QUEST | Camp Shirts | BRENT BINNELL; brent.binnal@gmail.com; 909-331-1777
LITTLE DEBBIE | Foods | McKee Foods
AMERCIAN BEDDING | Mattress, bed frames, etc. | americanbeddingmfg.com
AMERICAN CAMP ASSOCIATION | Accreditation, training, resources | acacamps.org
HERITAGE HEALTH FOOD | Vegefoods | Jay Jones jjones@heritagehealthfood.com 423-238-4211
MARANATHA VOLUNTEERS INT'L | NAD volunteer projects | David Woods dwoods@maranatha.org 916-774-7750
TRINITY HPSI PURCHASING SERVICES | Save $$$ food and vendors | Mike Moulton mike.moulton@trinity-usa.net 615-672-0229
ULTRACAMP | Online registration, etc. | www.ultracamp.com 888-791-2080
SYSCO FOODS | Foods
US FOODS | Foods
SLIP DISC MINISTRIES | Frizbee Golf' | Jackie Gibbs slipdisc.jackie@gmail.com
CHRISTIAN CAMPING INTERNATIONAL | Resources for Christian Camps | info@ccca.org 719-260-9400
24
VENDOR PROTOCOL
WHO ARE THEY?
These guests are those who provide valuable services to our camps (classes, materials, resources, etc.).
OUR GOALS WITH VENDORS
1) Make sure they have adequate time to connect with our members
2) Provide the opportunity for them to stay for the entire convention, if desired. It’s their chance to connect with us and us with them. It is a ministry.
3) We need to do all we can to make them feel welcomed as a valued part of what we do at the convention and in our camp ministry.
4) Depending on their 'specialty', a vendor could be invited to present a seminar
FINANCIAL CONSIDERATIONS
1) Per Board Vote (12.3.17), there is no vendor (exhibitor) fee, and
2) To ask each vendor to provide $100 worth of ‘give-away’ at their exhibit, and
3) If staying at the convention, they would register and book their own lodging and meals
23

## Reg. Team
Registration Team Backtracking Timetable
Team Members
CHAIR |  | VP Communications
Members | 1 | E-News Editor
| 2 | Host Camp 'Registrar'
3
4
5
MONTH | # | TO DO LIST
FEBRUARY | 1 | All Teams: CREATE TENTATIVE CONVENTION SCHEDULE
MARCH | 1 | All Teams: WORK WITH NAD CAMP CAMP DIRECTOR IN SECURING GUEST SPEAKER(S)
GUEST SPEAKERS
Opening Session - Traditionally the Local Conference President
General Sessions - Pastor, Conference Official (local to GC), other specialty field (counseling, etc.)
MAY | 1 | All Teams: FINALIZE CONVENTION SCHEDULE
| 2 | Set up Online Registration with Ultracamp based on Host Camp and Convention Needs
| 3 | Provide registration link to E-News
REGISTRATION - is done through UltraCamp.
| 1 | The goal is to have this site up and running by May 31st
| 2 | Connect with UltraCamp for any additional set up or change that we can't accomplish
| 3 | Make this site available to the Host Camp so they can keep updates on registrations
| 4 | Determine when online registration should close
| 5 | Advertise and promote the convention registration through E-News and on Website
NO SUMMER ASSIGNMENTS
August 20th | 1 | All Teams: AS IT BECOMES AVAILABLE CONTINUE TO PROVIDE INFORMATION TO E-NEWS TO PROMOTE THE CONVENTION
7 to 8 weeks | 1 | All Teams: PREPARE LIST OF QUESTIONS FOR ONLINE CONVENTION SURVEY: Big Ideas, Suggestions & Observations, Value
| 2 | Have announcement in E-News about the posting of Job Openings, Wanted, For Sale at the Convention
5 to 6 weeks | 1 | Locate Welcome - Information Center Host…could be a host camp staff
18
4 weeks | 1 | Communicate with host camp special meals
| 2 | Communicate with host camp current lodging needs
| 3 | Order name badges
3 weeks | 1 | Last minutes items for E-News- Giveaways, etc.
| 2 | Update meal & lodging needs and share with host camp
2 weeks | 1 | All Teams: SHIP ANY SUPPLIES TO HOST CAMP
| 2 | Print Name Badges
| 3 | Purchase paper, pens
| 4 | Obtain Tickets for Free Drawing
| 5 | Update meal & lodging needs and share with host camp
1 week | 1 | Update meal & lodging needs and share with host camp
1 to 2 days | 1
| 2 | Set up Membership List Update
| 3 | Set up Job Openings, For Sale Bulletin Board (work with host camp)
| 4 | Set up welcome - information center with hot drinks, snacks, maps, etc.
ONSITE CHECK-IN GOALS
| 1 | Make this convenient and quick
| 2 | Post 'open' hours after normal registration closes
| 3 | Make sure those coming in late at night can 'register' and get keys to lodging
CONVENTION | 1 | Register Guests: Include Free Drawing Ticket, map of camp, program brochure, pen, paper, 'freebie gift', etc.
| 2 | Finalize Registration Discrepancies
| 3 | Prepare attendance summary for AACP Board
| 4 | DEBRIEF CONVENTION WITH BOARD (during last breakfast)
Post-Convention | 1 | All Teams: SEND OUT THANK YOU LETTERS: Exhibitors, Presentors, Speakers, Host Camp, Volunteers, Staff, Sponsors, Food Service, etc.
| 2 | All Teams: DISCUSS WAYS TO IMPLEMENT SUGGESTIONS
CONFERENCE CALL PROCEDURES - See page 10
PURCHASING & REIMBURSEMENTS - See page 10
19

## Prog Team
Programming Team Backtracking Timetable
Team Members
CHAIR |  | VP for Conventions
Members | 1 | VP for Conventions (Elect)
| 2 | AACP President
| 3 | AACP President-Elect
| 4 | Vendor Coordinator
5
MONTH | # | TO DO LIST
FEBRUARY | 1 | All Teams: CREATE TENTATIVE CONVENTION SCHEDULE
| 2 | Secure Corporate donors: non-cash…books, gift bags, pens, balloons, high end giveaway, free convention, etc.
| 3 | Work on Convention Theme woven throughout program
MARCH | 1 | All Teams: WORK WITH NAD CAMP CAMP DIRECTOR IN SECURING GUEST SPEAKER(S)
| 2 | Select Speaker(s) General Session - finalize $$$ with NAD Camp Director
| 3 | Invite host conference president to speak on opening night
GUEST SPEAKERS
Opening Session - Traditionally the Local Conference President
General Sessions - Pastor, Conference Official (local to GC), other specialty field (counseling, etc.)
APRIL | 1 | VENDOR - contact potential vendors for exhibits
VENDOR PROTOCOL
WHO ARE THEY?
These guests are those who provide valuable services to our camps (classes, materials, resources, etc.).
OUR GOALS WITH VENDORS
1) Make sure they have adequate time to connect with our members
2) Provide the opportunity for them to stay for the entire convention, if desired. It’s their chance to connect with us and us with them. It is a ministry.
3) We need to do all we can to make them feel welcomed as a valued part of what we do at the convention and in our camp ministry.
4) Depending on their 'specialty', a vendor could be invited to present a seminar
FINANCIAL CONSIDERATIONS
1) Per Board Vote (12.3.17), there is no vendor (exhibitor) fee, and
2) To ask each vendor to provide $100 worth of ‘give-away’ at their exhibit, and
3) If staying at the convention, they would register and book their own lodging and meals
20
MAY | 1 | All Teams: FINALIZE CONVENTION SCHEDULE
| 2 | Secure Music Leader(s) - check with host camp
| 3 | Select Afterglow Host
| 4 | VENDOR - contact potential vendors for exhibits
WORSHIP FORMAT
FREE DRAWINGS on projection screen
Songs & Singing
Prayer Time
Introduction of Speaker
Speaker
Prayer
Announcements
NO SUMMER ASSIGNMENTS
August 20th |  | All Teams: AS IT BECOMES AVAILABLE CONTINUE TO PROVIDE INFORMATION TO E-NEWS TO PROMOTE THE CONVENTION
SEPTEMBER | 1 | Determine Holiday Decorations …work with host camp
| 2 | Determine any extra signs that are needed for the convention, Work with host camp
| 3 | Check with AACP Board for any AACP awards to be presented (Norm Middag Awards, NAD special awards, Retirees, etc)
| 4 | VENDOR - contact potential vendors for exhibits
AWARDS
NAD Recognition Awards - As voted by the Board
AACP Awards
Norm Middag Award of Excellence
7 to 8 weeks | 1 | All Teams: PREPARE LIST OF QUESTIONS FOR ONLINE CONVENTION SURVEY: Big Ideas, Suggestions & Observations, Value
| 2 | Order any special 'freebies'
| 3 | Final Vendor Checklist to Host Camp
| 4 | Work with Host Camp to provide Child Care
5 to 6 weeks | 1 | Put together 'Good Morning, AACP' morning program features
| 2 | Plan Communion Service
GOOD MORNING AACP!
FREE DRAWINGS on projection screen
Songs & Singing
Prayer Time
Guest Interviews (2-3, depending on allotted time)
Prayer
Announcements
4 weeks | 1 | VENDOR - final list completed 21
3 weeks | 1 | Last minute Items for E-New
2 weeks | 1 | All Teams: SHIP ANY SUPPLIES TO HOST CAMP
| 2 | Print Schedule/ Brochure
1 week | 1 | Prepare Online Convention Survey
CONVENTION | 1 | Open online convention survey
| 2 | Compile Results of Convention Survey (last day)
| 3 | VENDORS: Host Exhibitors
DEBRIEF CONVENTION WITH BOARD (during last breakfast)
Post-Convention | 1 | SEND OUT THANK YOU LETTERS: Exhibitors, Presentors, Speakers, Host Camp, Volunteers, Staff, Sponsors, Food Service, etc.
| 2 | Compile all survey results and share at January's Board Meeting
| 3 | DISCUSS WAYS TO IMPLEMENT SUGGESTIONS
CONFERENCE CALL PROCEDURES - See page 10
PURCHASING & REIMBURSEMENTS - See page 10
22

## Ed Team
Education Team Backtracking Timetable
CHAIR |  | Asst. VP for Conventions
Members | 1 | NAD Resource Coordinator
2
3
4
5
MONTH | # | To Do List
FEBRUARY | 1 | All Teams: CREATE TENTATIVE CONVENTION SCHEDULE
| 2 | Select Track Leaders: 1) Activities, Attractions & Camp Store 2) Summer Camp Directors 3) Camp Services (Guest Services, Registration, Housekeeping, Janitoria) 4) Camp Spouses 5) Food Service 6) Managers & Executive Directors 7) Summer Camp Staff 8) Ranger, Maintenance, Vehicles 9) New to Camp 10) ACA Accreditation
| 3 | Discuss seminar topic possibilities
MARCH | 1 | All Teams: WORK WITH NAD CAMP CAMP DIRECTOR IN SECURING GUEST SPEAKER(S)
| 2 | Track Leaders contact seminar presenters
GUEST SPEAKERS
Opening Session - Traditionally the Local Conference President
General Sessions - Pastor, Conference Official (local to GC), other specialty field (counseling, etc.)
APRIL | 1 | Track Leaders contact seminar presenters
MAY | 1 | FINALIZE CONVENTION SCHEDULE
| 2 | Track Leaders contact seminar presenters
NO SUMMER ASSIGNMENTS
August 20th |  | AS IT BECOMES AVAILABLE CONTINUE TO PROVIDE INFORMATION TO E-NEWS TO PROMOTE THE CONVENTION
SEPTEMBER | 1 | Track Leaders contact seminar presenters
| 2 | Obtain seminar descriptions
7 to 8 weeks | 1 | PREPARE LIST OF QUESTIONS FOR ONLINE CONVENTION SURVEY: Big Ideas, Suggestions & Observations, Value
| 2 | Make sure recording devices are functioning properly
| 3 | Obtain 'needs' list from seminar presenters 25
3 weeks | 1 | Last minutes Items for E-News
| 2 | Seminar Presenters: remind about handouts, if needed to be copied ahead of time OR at camp
2 weeks | 1 | All Teams: SHIP ANY SUPPLIES TO HOST CAMP
| 2 | Create packing list
CONVENTION | 1 | Set out recording devices
| 2 | All Teams: DEBRIEF CONVENTION WITH BOARD (during last breakfast)
Post- Convention | 1 | All Teams: SEND OUT THANK YOU LETTERS: Exhibitors, Presentors, Speakers, Host Camp, Volunteers, Staff, Sponsors, Food Service, etc.
| 2 | All Teams: DISCUSS WAYS TO IMPLEMENT SUGGESTIONS
CONFERENCE CALL PROCEDURES - See page 10
PURCHASING & REIMBURSEMENTS - See page 10
26

## Host Team
Host Camp Team Backtracking Timetable
CHAIR |  | Camp Director or Assigned
Members | 1 | Food Service
| 2 | Housekeeping/Janitorial
| 3 | Guest Services/Registration
4
5
MONTH | # | To Do List
FEBRUARY | 1 | CREATE TENTATIVE CONVENTION SCHEDULE
MARCH | 1 | WORK WITH NAD CAMP CAMP DIRECTOR IN SECURING GUEST SPEAKER(S)
| 2 | Locate potential 'Local Attractions' for Pre and Post Convention options for attendees & share with E-News
| 3 | Provide airport options to E-News
GUEST SPEAKERS
Opening Session - Traditionally the Local Conference President
General Sessions - Pastor, Conference Official (local to GC), other specialty field (counseling, etc.)
NO SUMMER ASSIGNMENTS
SEPTEMBER | 1 | Provide E-News with 'directions to camp' & 'other information'
7 to 8 weeks | 1 | PREPARE LIST OF QUESTIONS FOR ONLINE CONVENTION SURVEY: Big Ideas, Suggestions & Observations, Value
| 2 | Determine potential Free Time Activities
| 3 | Obtain Vendor List and needs outline from Programming to accommodate them in display area
| 4 | Locate Child Care providers
| 5 | Provide for a Camp Tour During Convention
5 to 6 weeks | 1 | Determine Location of Union Meetings
| 2 | Finalize Evening Recreation
4 weeks | 1 | Obtain tentative speciall meal list for food service
| 2 | Obtain current lodging needs list
3 weeks | 1 | Last minute items for E-News
2 weeks | 1 | Finalize PA operation & IT services for general sessions 31
1 to 2 days | 1 | In meeting area, set up "Free Drawing Tables"
| 2 | Set up meeting rooms
| 3 | Seminar Presenter needs taken care of
CONVENTION | 1 | Oversee Room Assignments
| 2 | Host Exhibitor Area
| 3 | Provide for housekeeping needs
| 4 | DEBRIEF CONVENTION WITH BOARD (during last breakfast)
Post- Convention | 1 | All Teams: SEND OUT THANK YOU LETTERS: Exhibitors, Presentors, Speakers, Host Camp, Volunteers, Staff, Sponsors, Food Service, etc.
| 2 | All Teams: DISCUSS WAYS TO IMPLEMENT SUGGESTIONS
CONFERENCE CALL PROCEDURES - See page 10
PURCHASING & REIMBURSEMENTS - See page 10
32

## Promote
PROMOTING THE EVENT
E-NEWS PROMOTION
Each month should contain some promotion/information on the convention. Here are some ideas that could be used:
| January | Mark Your Calendars - Here's the Date
| February | Convention Location with pictures and accomodations
| March | Convention's nearby attractions for vacation possibilities
| April | Guest Speaker(s) with pictures
| May | Registration Now Open
| June | Sample of Seminar Titles
| July | Sample of Seminar Titles
| August | Don't Forget to Register
| September | Vacation - come early, stay late
| October | Register before the deadline
| November | Bring Camp Give-Aways
| December | Join Us at Next Year's Convention!
WEB SITE INFORMATION
This site can be added to as the information becomes available. It should contain the following:
Dates
Cost for Adults/Children
Location of Event
Closest Airports
Local Attractions
Map to camp
Accomodations
Meals
Registration Link
Guest Speaker(s) Profile & Picture
Seminar Titles
Convention Schedule
Board Meeting Specifics
Business Meeting Agenda Items (if available)
On Site Activities
Day Care/Child Care information, if provided
Special Features or Highlights during or at the Convention
Vendor Exhibits
Other Motivations for Attending
35